3GPP GERAN TSG#22 	GP-042836

Cape Town, 8-12 November 2004

Source: Rapporteur (Marc Grant, Cingular Wireless)

3GPP TR 50.099 V0.42 (2004-04)

Technical Report

3rd Generation Partnership Project;

Technical Specification Group GERAN;

Project scheduling and open issues for GERAN;

The present document has been developed within the 3rd Generation Partnership Project (3GPP TM) and may be further elaborated for the purposes of 3GPP.	 
The present document has not been subject to any approval process by the 3GPP Organizational Partners and shall not be implemented.	 
This Specification is provided for future development work within 3GPP only. The Organizational Partners accept no liability for any use of this Specification.
Specifications and reports for implementation of the 3GPP TM system should be obtained via the 3GPP Organizational Partners' Publications Offices.

.

.

Keywords

<GERAN, work plan, project schedule]>

3GPP

Postal address

3GPP support office address

650 Route des Lucioles - Sophia Antipolis

Valbonne - FRANCE

Tel.: +33 4 92 94 42 00 Fax: +33 4 93 65 47 16

Internet

http://www.3gpp.org

Copyright Notification

No part may be reproduced except as authorized by written permission.
The copyright and the foregoing restriction extend to reproduction in all media.

© 2004, 3GPP Organizational Partners (ARIB, ATIS, CCSA, ETSI, TTA, TTC).

All rights reserved.

Contents

1	Scope	5

2	Open Work item status and approval time frame	5

2	Completed or Terminated Work items	10

Annex A : Change history		15

# 1	Scope

The purpose of this document is to capture status of all TSG GERAN work items in order for the group to get an overview of current ongoing work. The status and progress on the different work items are partly captured from the GERAN2 work plan, partly from agreements in the plenary sessions.

This TR is used as a mean to provide input to the complete 3GPP work plan that is handled by MCC.

# 2	Open Work item status and approval time frame

This list reflects the open work items running under the responsibility of TSG GERAN.

|  | Work items in this colour are closed or building blocks. |
| --- | --- |

| Feature | Building block | - Work task | Level of completion | Start Date | Date of completion | Status |
| --- | --- | --- | --- | --- | --- | --- |
| Alignment of 3G functional split and Iu (GER3GAL) GP-021256 | GERAN user / control plane (GER3GAL-GUCOPL) GP-021255 | - Alignment with UMTS bearer concept - Stage 2 |  | Aug 2000 | Jun 2001 | Ready for R5. |
|  |  | - Adoption of the UTRAN PDCP |  |  | Dec 2001 |  |
|  |  | - Development of RLC / MAC |  |  | Aug 2002 |  |
|  |  | - Development of GERAN RRC |  |  | Jun 2002 |  |
|  |  | - Ciphering and integrity protection concept paper |  |  | Apr 2002 |  |
|  |  | - Multiple TBF or equivalent Concept paper |  |  | Feb 2002 |  |
|  |  | - Paging concept |  |  | Apr 2002 |  |
|  |  | - Dedicated physical subchannels. Includes traffic and control channels |  |  | Nov 2001 |  |
|  |  | - Iu support and broadcast concept |  |  | Apr 2002 |  |
|  |  | - Impact of using RLC instead of LAPDm concept |  |  | Feb 2002 |  |
|  |  | - Contention resolution, mobile-station identity, and access concept |  |  | Nov 2001 |  |
|  |  | - PDCP concept |  |  | Apr 2002 |  |
|  |  | - Downlink delayed TBF release |  |  | Aug 2002 |  |
|  |  | - Add transparent RLC Concept |  |  | Feb 2002 |  |
|  |  | - Handover concept |  |  | Feb 2002 |  |
|  |  | - Physical layer alignment with UMTS bearer concept - Control channels in 45.003 - Receiver performance in 45.005 for PDTCH/TCH and control channels |  |  | Jun 2001 |  |
|  | Iu rg interface (GER3GAL-Iurg) GP-010428 | - Inter BSS interface - Identification of requirements - Stage 2 - Adoption of relevant parts from Iu r - Complementation with GERAN specifics - New stage 3 |  | Nov 2000 | Jun 2002 | Ready for R5. Closed |
|  |  | - Inter BSS-RNS interface - Identification of requirements - Stage 2 - Adoption of relevant parts from Iu r - Complementation with GERAN specifics - New stage 3 |  |  | Jun 2002 | Ready for R5. Closed |
|  | Voice over GERAN PS and CS concept GP-021252 | - Voice over GERAN PS and CS concept - Architecture for A, Iu cs and Iu ps - Handover - RTP payload |  | Nov 2000 | Nov 2001 | Ready for R5. Closed |
|  | GERAN MS Conformance test for GERAN interface bevolution GP-021253 | - MS test | 0% | August 2003 |  | Under evaluation |
|  | GERAN BTS Conformance test for GERAN interface evolution GP-021254 | - BTS test | 0% | August 2003 |  | Under evaluation |
| Enhancement of Broadcast and Introduction of Multicast (in responsibility of TSG SA1) | Support of the Multimedia Broadcast Multicast Service (MBMS) in GERAN (MBMS-GERAN) GP-022566 | - Impact on the logical and physical channels - Simultaneous support of MBMS services - Simultaneous support of MBMS and non-MBMS services - Resynchronisation at cell change - Decision making process between point-to-point or point-to-multipoint configurations - MBMS channel allocation procedures to multiple MSs - Changes to the Gb interface - GERAN-specific changes to the Iu-ps interface - Interaction between MBMS and Iu-flex - Security aspects - MS conformance tests | 85% | November 2002 | January 2005 | Started |
| Multiple TBF in A/Gb mode (MULTBF) GP-021263 | Multiple TBF in A/Gb mode (MULTBF-Agbmode) GP-021263 | - Multiple TBF Concept paper - Multiple TBF Stage 2 (43.064) CRs - Multiple TBF Stage 3 (44.060) CRs | 100% | April 2002 | August 2003 | Completed |
|  | Multiple TBF in A/Gb mode – MS testing GP-022098 | - MS conformance tests | 0% |  |  | Under Evaluation |
| Flexible Layer One for GERAN (FLOGER) GP-021018 | Realisation of a Flexible Layer One (FLOGER-Real) GP-021019 | - Technical Report - Architecture in 45.001 and 43.051 - Multiplexing in 45.002 - Channel Coding in 45.003 - Performance Requirements in 45.005 - Radio subsystem link control in 45.008 - Requirements in 44.004 | 100% | April 2002 | April 2004 | Completed |
|  | Signalling and protocol support for a Flexible Layer One (FLOGER-SigPro) GP-021020 | - Modifications to RLC/MAC in 44.060 and 44.160 - Modifications to RRC in 44.118 and 44.018 | 100% | October 2002 | June 2004 | Completed |
|  | Security for a Flexible Layer One (FLOGER-SecFLO) GP-021021 | - Ciphering in 44.160,44.118, 44.060 and 44.018 | 100% | February 2003 | August 2003 | Completed |
|  | GERAN MS Conformance test for the Flexible Layer One (FLOGER-Msconf) GP-021022 | - MS Test in 51.010 | 0% | February 2004 |  | Under Evaluation |
|  | GERAN BTS Conformance test for the Flexible Layer One (FLOGER-BTSconf) GP-021023 | - BTS Test in 51.021 | 0% | February 2004 |  | Under Evaluation |
| Addition of frequency bands to GSM (TAPS) GP-022072 | Addition of frequency bands to GSM – Changes to core specs (TAPS-Specs) GP-022073 | - New frequency ranges - Scenarios for new frequencies - Classmark information elements - Add frequency ranges - Add frequency and channels - Add frequency ranges - 43.022 Add channels to be searched | 100% | June 2002 | Dec 2002 | Ready for Rel-6 |
|  | Addition of frequency bands to GSM – Changes for conformance tests (TAPS-Conf) GP-022074 | - 51.010-1 Add testing | 0% |  | November 2004 | Not Started |
| Enhanced Power Control (EPC) GP-012748 | Realization of Enhanced power control and signaling support GP-012749 | - Concept - Changes to 43.051 - Changes to 44.004 - Changes to 44.018 - Changes to 48.058 - Changes to 45.001 - Changes to 45.002 - Changes to 45.003 - Changes to 45.008 |  |  | Nov 2001 | Ready for Rel 5. Closed |
|  | GERAN MS Conformance test for Enhanced Power Control GP-012750 | - MS test | 0% |  |  | Under Evaluation |
|  | GERAN BTS Conformance test for Enhanced Power Control GP-012751 | - BTS test | 0% |  |  | Under Evaluation |
| 8PSK AMR HR (8PSK-AH) GP-012752 | Definition of channel coding, performance requirements and signaling support GP-012753 | - Concept - Changes to 44.018 - Changes to 45.001 - Changes to 45.002 - Changes to 45.003 - Changes to 45.005 - Changes to 24.008 - Changes to 48.058 |  | Dec 2001 | Jun 2002 | Ready for R5. Closed |
|  | GERAN MS Conformance test for 8PSK HR GP-012754 | - MS test | 0% |  |  |  |
|  | GERAN BTS Conformance test for 8PSK HR GP-012755 | - BTS test | 100% |  | Dec 2002 |  |
| Wideband telephony services (UMTS) | Support of WB AMR in GERAN (GAMRWB) GP-000453 | - GMSK and 8PSK WB FR / HR support - Channel coding in 45.003 - Signalling for A interface - Signalling for Iu - Link adaptation in 45.009 - Receiver performance in 45.005 |  | January 2000 | Apr 2002 Nov 2001 Jun 2002 | Ready for R5. Closed |
|  | GERAN MS Conformance test for WB AMR GP-000454 | - MS test | 0% |  |  | Under Evaluation |
|  | GERAN BTS Conformance test for WB AMR GP-000455 | - BTS test | 100% |  | Dec 2002 | Closed |
| Single Antenna Receiver Interference Cancellation (SAIC) GP-023400 | Single Antenna Receiver Interference Cancellation (SAIC) | - Determine feasibility of SAIC for GMSK and 8PSK scenarios under realistic synchronized and non-synchronized network conditions. Using a single Feasibility Study, both GMSK and 8PSK scenarios will be evaluated individually. - Realistic DIR (Dominant-to-rest of Interference Ratio) levels and distributions based on network simulations and measurements. - Robustness against different training sequences. - Determine method to detect/indicate SAICcapability. | 100% | Nov 2002 | August 2004 | Closed |
| Uplink TDOA location determination for GSM, CS domain GP-032773 | Uplink TDOA location determination for GSM, CS domain | - Addition of U-TDOA in the CS domain | 100% | November 2002 | April 2004 | Completed, except for potential LMU performance specs. |
| Uplink TDOA location determination for GPRS, PS domain GP-032774 | Uplink TDOA location determination for GPRS, PS domain | - Addition of U-TDOA in the PS domain | 100 | June 2003 | November 2004 | Started |
| Support of Conversational Services in A/Gb mode via the PS domain (SCSAGB) GP-030443 | Creation of a Technical Report (SCSAGB-TR) GP-030444 | - Technical Report | 100% | Feb 2003 | November 2003 | Completed |
|  | Stage 2 (SCSAGB-Stage2) GP-030445 | - PS handover - SNDCP/LLC compression - Definition of radio resource management functionality - Modifications to FLO - Radio channel support | 85% | Nov 2003 | January 2005 | Started |
|  | Radio Channel Support (SCSAGB-RCS) GP-030446 | - Radio channel support for Conversational QoS - Introduction of continuous measurement reporting | 0% | Feb 2004 | November 2005 | Not Started |
|  | Definition of radio resource management functionality (SCSAGB-RRM) GP-030447 | - Addition/modification of radio resource management protocol layer | 0% | Feb 2004 | November 2005 | Not Started |
|  | PS Handover (SCSAGB-PSH) GP-030448 | - BSSGP procedures for change of BSC - Bi-Casting - Context transfer | 25% | Feb 2004 | January 2005 | Not Started |
|  | Modifications to FLO (SCSAGB-FLO) GP-030449 | - FLO specific impacts due to conversational QoS | 0% | Feb 2004 | November 2005 | Not Started |
| Alignment between the test-regimes for GERAN capable MS GP-032236 |  | - Determine the controversial test cases in the different test regimes and align them with 3GPP GERAN test specifications. Such test cases to be added to TS 51.010. | 80% | June 2003 | September 2004 | Started |
| Downlink Advanced Receiver Performance (DARP) GP-041966 | DARP test scenarios GP-041967 | - Interference test cases for 45.005 | 100% | November 2003 | September 2004 | Started |
|  | DARP for GMSK modulated voice services GP-041968 | - Performance Requirements in 45.005 - Radio subsystem link control in 45.008 | 100% | February 2004 | November 2004 | Started |
|  | DARP for GPRS and EGPRS MCS1-MCS4 GP-041969 | - Performance Requirements in 45.005 - Radio subsystem link control in 45.008 | 100% | February 2004 | November 2004 | Started |
|  | DARP Capability signalling GP-041970 | - Modification of 24.008 for signalling of MS ARP capability | 100% | November 2003 | September 2004 | Started |
|  | GERAN MS Conformance test for ARP GP-041971 | - MS Test in 51.010 | 20% | August 2004 | February 2005 | Started |
| Reduction of PS service interruption in Dual Transfer Mode (PSintDTM) GP-032548 | Reduction of PS service interruption in Dual Transfer Mode / Use case and requirement definition (PSintDTM-Req) GP-032549 | - Study of use cases and requirements. - Areas for investigation are: - Cell change scenarios - CS channel establishment during PS session - CS channel release during PS session | 100% | November 2003 | April 2004 | Started |
|  | Reduction of PS service interruption in Dual Transfer Mode / Performance Study of Current Procedures (PSintDTM-Perf) GP-032550 | - Analyse performance of the common use cases to determine to what extent improvements are needed to the DTM procedures in GPRS. | 100% | November 2003 | April 2004 | Started |
|  | Reduction of PS service interruption in Dual Transfer Mode / Reduction of service interruption times and packet loss during Dual Transfer Mode and mobility procedures (PSintDTM-Reduct) GP-032551 | - Investigate changes needed to improve DTM procedures identified in this work item. | 100% | February 2004 | November 2004 | Started |
|  | Reduction of PS service interruption in Dual Transfer Mode / MS Conformance testing | - MS Conformance testing (51.010) | 0% | June 2004 |  | Under Evaluation |
|  | Reduction of PS service interruption in Dual Transfer Mode / BTS Conformance testing | - BTS Conformance testing | 0% | June 2004 |  | Under Evaluation |
| FS: Generic Access to A/Gb Interface (GP-041592) (GAAG) | Generic Access to A/Gb Interface | Determine the feasibility of generic IP based access to A/Gb interface. | 100% | January 2005 | January 2005 | Not Started |
| Global Navigation Satellite Systems (GNSS) (GP-0422268) | Support for GNSS in GERAN | To include the capability of Assisted GALILEO as an Assisted GNSS into the GERAN. | 0% | April 2005 | April 2005 | Not Started |
| FS of enhanced support of Video Telephony (GP-042221) (VIDGER) | Feasibility study of enhanced support for video telephony service over GERAN via the A interface | To enhance performance of video telephony service over GERAN via the A interface. | 10% | January 2005 | April 2005 | Not Started |
| Generic Access to the A/Gb Interface (GP-042247) (GAAI) | Generic IP based Access to A/Gb interface – Stage 2 | Stage 2 for Generic Access to the A/Gb Interface | 75% | April 2005 | April 2005 | Not Started |
|  | Generic IP based Access to A/Gb interface – Stage 3 | Stage 3 for Generic Access to the A/Gb Interface | 0% | April 2005 | April 2005 | Not Started |
|  | MS Conformance Test for Generic Access to A/Gb Interface | MS Conformance Test for Generic Access to A/Gb Interface | 0% | June 2005 | June 2005 | Not Started |
| Enhancements of VGCS in public networks for communication of public authority officials GP-041837 (EVGCS) | Enhancements of VGCS in public networks for communication of public authority officials | Enhancements of VGCS in public networks for communication of public authority officials | 0% | April 2005 | April 2005 | Not Started |

# 2	Completed or Terminated Work items

This list reflects work items that have been completed or terminated.

| Feature | Building block | Work task | Level of completion | Start Date | Date of completion | Status |
| --- | --- | --- | --- | --- | --- | --- |
| GERAN/UTRAN interface evolution 1 GP-000481 | Evolution of Iu ps | - Identification of GERAN requirements on Iu ps - Update of specifications |  |  | Nov 2001 Mar 2002 | Ready for R5. Closed |
| GERAN/UTRAN interface evolution 2 GP-010417 | Evolution of Iu cs GP-000430 | - Identification of GERAN requirements on Iu cs - Update of specifications |  |  | Apr 2002 Jun 2002 | Ready for R5. Closed |
| Low chip rate TDD option (UTRAN) | Low chiprate TDD interworking with GERAN GP-000432 | - Handover and Cell Selection / Reselection to UTRA 1.28Mcps TDD |  |  |  | Ready for R4. Closed |
| GERAN improvements 1 GP-000433 | Gb over IP GP-000434 | IP-fication of Gb - Concept - Changes to 08.16, 08.18 |  |  |  | Ready for R4. Closed |
| GERAN improvements 3 GP-010909 | Evolution of the transport for A GP-010910 | - Definition of a new A/Ater Interface Transport Layer option based on the Iu Interface Transport Layer - Adaptation of the Layer 3 BSSMAP procedures as required. | 0% |  | Dec 2002 | Terminated. Not standardised |
| GERAN Improvements 4 GP-010363 | Gb enhancements 2 GP-010363 | Stage 2 Stage 3 (changes in 44.060) - Definition of enhanced countdown procedure - Definition of enhanced TBF release procedure |  |  |  | Ready for R4. Closed |
| GERAN Inter BSC NACC improvements over the Gb Interface GP-012313 | Modification of Gb protocols for GERAN Inter BSC NACC over the Gb interface GP-012314 | Stage 3 (changes to ) 48.018 |  |  | Apr 2002 | Ready for R5. Closed |
|  | Modification of core network protocols for GERAN Inter BSC NACC for Gb interface GP-011877 | Stage 2 - Concept - 23.060 change – Definition of Inter BSC NACC Stage 3 (changes to ) - 29.060 |  |  | Nov 2001 Apr 2002 |  |
| GERAN support for IP multimedia GP-010420 | GERAN Header adaptation GP-010421 | Header adaptation: - Definition of compression for PDCP protocol - Conceptual description in stage 2 - Necessary changes on stage 3 | 100% |  | Sept 2000 Oct 2001 Dec 2002 | Ready for Rel-5. Closed |
|  | GERAN Radio access bearer design for IP multimedia GP-010422 | MuM control signalling for conversational multimedia services. - Identification of requirements - Necessary modifications due to SIP | ?% |  | Feb 2002 Dec 2002 | Terminated. Not standardised |
|  | GERAN MS Conformance test for support of IP multimedia GP-010424 | - MS test | 0% |  | Dec 2002 | Terminated. Not standardised |
|  | GERAN BTS Conformance test for support of IP multimedia GP-010425 | - BTS test | 0% |  | Dec 2002 | Terminated. Not standardised |
| Flow control supporting an MS with multiple data flows with different QoS over the Gb interface GP-021767 | Update of stage 2 specifications | - Concept document 23.060 (changes to) – Flow Control |  |  | June 2002 June 2002 | Closed |
|  | Modification of BSSGP protocol GP-021508 | Stage 3 (changes to ) - 48.018 |  |  | June 2002 | Ready for release 5. Closed |
| GERAN enhancements for streaming services 1 GP-010429 | GERAN enhancements for streaming services 1 GP-010429 | - Concept - RLC protocol enhancement (SDU Discard) |  |  | Oct 2001 Nov 2001???? | Ready for R5. Closed |
| GERAN enhancements for streaming services 2 GP-010430 | GERAN enhancements for streaming services 2 GP-010430 | Usage of ECSD Stage 2 Stage 3 - RLC PDU formats - MAC header |  |  | Jun 2001 Jun 2002 | Ready for R5. Closed |
| Intra Domain Connection of RAN Nodes to Multiple CN Nodes: Overall System Architecture SA2 Feature | GERAN work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes GP-020492 | Stage 2 (changes to ) - 43.051 Introduction of support for IDNNS in GERAN Iu mode Stage 3 (changes to ) - 48.016 Use of Gb interface concepts when a network applies IDNNS - 48.018 Include MSC/VLR identity in CS IMSI paging |  |  | Jun 2002 | Ready for R5. Closed, accept changes for Gb over IP |
| Real Time QoS for packet services including VoIP (UTRAN) | HOs: maintenance of real-time QoS while moving between cells in the PLMN including inter-SGSN change and SRNS relocation or possibly other mechanisms (UTRAN) GP-010431 | Handover for the packet switched domain - Stabile RT handover report 25.936 including header removal - Update of stage 2 - Update of relevant stage 3 specs |  |  | Nov 2001 | Closed |
| Uplink TDOA feasibility study GP-012794 | Uplink TDOA feasibility study GP-012794 | - Performing of a feasibility study |  |  | Jun 2002 | Closed for R6. |
| 700 MHz spectrum support GP-000449 | GERAN support for the 700 MHz band | - Signaling support - Physical layer definitions - Receiver performance and RF budget |  |  |  | Ready for R4. Closed |
|  | GERAN MS Conformance test for 700 MHz band GP-000451 | - MS test |  |  | Jun 2001 | Closed |
|  | GERAN BTS Conformance test for GERAN interface evolution GP-000452 | - BTS test | 100% |  | Dec 2002 | Closed |
| Enhanced A/Gb feasibility study GP-022565 | Enhanced A/Gb feasibility study GP-022565 | - Requirements for the support of conversational services - Identification of the different building blocks for the provision of conversational services on the existing A/Gb protocol stack - Outline of impact and feasibility of these building blocks and their different solutions - Impact on 3GPP architecture and requirement to co-ordinate with other TSGs (CN, SA) - Standardisation effort - Dependency to other features | 100% |  | Nov 2002 | Closed at GERAN #13 |
| MS Conformance Testing of Dual Transfer Mode GP-023236 | MS Conformance Testing of Dual Transfer Mode | - MS Conformance Testing of Dual Transfer Mode | 100% |  | Feb 2003 | Closed at GERAN #14 |
| Location service (UMTS) | LCS interoperability aspects to GERAN GP-000456 | - Co-ordinated development of GSM LCS Phase 2 and UMTS LCS, S2 and GERAN |  |  |  | Ready for R5. Closed |
|  | Location service for GERAN R4 GP-010932 | - Work for aligning LCS R4 CN and GERAN |  |  |  | Ready for R4. Closed |
|  | Location Services (LCS) for GERAN in A/Gb Mode GP-011925 | - GERAN LCS Stage Two - Gb interface support for LCS - L3 protocol support for LCS - Stage 3 specifications |  |  | Feb. 2002 | Ready for Rel-5. Closed |
|  | Location Services (LCS) for GERAN in Iu Mode GP-011926 | - GERAN LCS stage 2 - Iu interface support for LCS - Iur-g interface support for LCS - RRC protocol support for LCS - Additional impacts on Broadcast of LCS data on packet channels - Stage 3 specifications |  |  | Stage 2-GERAN #8 Feb. 2002 Stage 3 – GERAN #9 Jun 2002 | Ready for R5. Closed |
|  | GERAN MS Conformance test for LCS (LCS-GERAN-Msconf) GP-000458 | - Develop LCS MS test case work plan (Release 98/99/4) - Develop LCS MS test cases | 100% |  | June 2003 | Completed |
|  | GERAN BTS Conformance test for LCS (LCS-GERAN-BTSconf) GP-000459 | - Develop LCS BTS test case work plan (Release 98/99/4) - Develop LCS BTS test cases | 0% |  | June 2004 | Closed without progress at GERAN #19 |
| Seamless support of streaming services in A/Gb mode (SSStrea) GP-022561 | Identification of requirements for streaming GP-022564 | - Requirements | 100% | August 2002 | August 2003 | Completed at GERAN #16 |
|  | Performance study of cell change mechanisms GP-022562 | - Performance of NACC - Performance of cell change in DTM for the PS domain - Handover | 100% | August 2002 | August 2003 | Completed at GERAN #16 |
|  | Reduction of service interruption times and packet loss during mobility procedures GP-022563 | - Optimisations of existing mechanisms/procedures - Inter-system NACC - PS Handover (within GERAN and between GERAN and UTRAN) - Dependency to other features | 100% | January 2003 | November 2003 | Completed at GERAN #17 |
|  | MS conformance testing GP-023424 | - MS conformance tests | 0% | September 2003 | January 2004 | Closed, no work needed. |
| GERAN improvements 2 (GEIMP2) GP-012812 | Gb enhancements GP-000436 | - Intra BSC NACC - Concept - Changes in 03.64 - Changes in 04.60 - Changes in 44.008 |  | Nov 2000 | June 2001 | Ready for R4. Closed |
|  | MS conformance test for Intra BSC NACC GP-012811 | - Changes in 51.010 | 100% | Nov 2001 | November 2003 | Completed at GERAN #17 |

Annex A : Change history

| Change history |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date | TSG # | TSG Doc. | Subject/Comment | Version |
| 23th February 2000 |  |  | First draft (V0.0.1) |  |
| 2nd April 2000 |  |  | Updated after GERAN #1 and EDGE WS #13 (V0.0.2) |  |
| 8th May 2000 |  |  | Updated after SMG2 #35 (V0.0.3) |  |
| 22nd May 2000 |  |  | Updated after SMG2 GERAN WS #2 (V0.0.4) |  |
| 24th May 2000 |  |  | Updated during SMG2 #36 (V0.0.5) |  |
| 2nd August 2000 |  |  | Updated for 3GPP S3 meeting (V0.0.6) |  |
| 28th August 2000 |  |  | Updated after SMG2 GERAN release 2000 and beyond Adhoc #1 |  |
| 9th October 2000 |  |  | Updated after TSG GERAN #1 as 50.099 (V0.0.1) |  |
| 6th November 2000 |  |  | Updated after TSG GERAN Adhoc on release 2000 and beyond #2 as 50.099 (V0.0.2) |  |
| 12th February 2001 |  |  | Updated after TSG GERAN #3 (V0.0.5) |  |
| April 2001 |  |  | Updated for TSG GERAN #4 (V0.06) |  |
| 7th May 2001 |  |  | Updated for TSG GERAN Adhoc on released 2000 and beyond #5 (V0.07) |  |
| 11th May 2001 |  |  | Updated during TSG GERAN Adhoc on release 2000 and beyond #5 (V0.08) |  |
| 28th May 2001 |  |  | Updated for TSG GERAN #5 (V0.09) |  |
| 27th August 2001 |  |  | Updated for TSG GERAN #6 (V0.10) |  |
| 26th Nov 2001 |  |  | Updated for TSG GERAN #7 (V0.11) |  |
| 30th Nov 2001 |  |  | Updated for TSG GERAN #7 (V0.12) |  |
| 30th Nov 2001 |  |  | Updated for TSG GERAN #7 (V0.13) |  |
| 15th April, 2002 |  |  | Updated for TSG-GERAN #9 (v0.15) |  |
| 19th April, 2002 |  |  | Updated for TSG-GERAN #9 (v0.16) |  |
| 24th June 2002 |  |  | Updated for TSG-GERAN #10 (V0.17) |  |
| 28th June 2002 |  |  | Updated during TSG GERAN #10 (V0.18) |  |
| 25th August 2002 |  |  | Updated for TSG GERAN #11 (V0.19) |  |
| 30th August 2002 |  |  | Updated during TSG GERAN #11 (V0.20) |  |
| 20th November 2002 |  |  | Updated during TSG GERAN #12 (V0.21) |  |
| 30th January 2003 |  |  | Updated for TSG GERAN #13 (v0.24) |  |
| 07th February 2003 |  |  | Updated during TSG GERAN #13 (v0.25) |  |
| 03th April 2003 |  |  | Updated for TSG GERAN #14 (v0.27). Aligned with WG2bis #13 work plan |  |
| 11th April 2003 |  |  | Updated during TSG GERAN #14 (v0.28). |  |
| 11th April 2003 |  |  | Updated during TSG GERAN #14 (v0.29). |  |
| 12th June 2003 |  |  | Updated for TSG GERAN #15 (v0.30). Aligned with WG2bis #14 work plan (v7.0). |  |
| 25th June 2003 |  |  | Updated during GERAN #15 (v0.31). Tdoc GP-0311727 |  |
| 27th June 2003 |  |  | Updated during end of GERAN #15 (v0.32). Tdoc GP-031731 |  |
| 28th August 2003 |  |  | Updated during GERAN #16 (v0.33). Tdoc GP-032286. |  |
| 5th November 2003 |  |  | Updated for GERAN #17 (v0.34). Aligned with WG2bis #16 work plan (v10.0) |  |
| 21st November 2003 |  |  | Updated during GERAN #17 (v0.35). Tdoc GP-032826 |  |
| 28th January 2004 |  |  | Updated for GERAN #18 (v0.36). Aligned with WG2bis #17 work plan (v12.1) |  |
| 6th February 2004 |  |  | Updated during GERAN #18 (v0.37). Aligned with WG2 #18 work plan (v13) |  |
| 16th April 2004 | G19 | GP-041052 | Updated for GERAN #19 (v0.38). Aligned with WG2bis #18 work plan (v14.0) | V0.38 |
| 23rd April 2004 | G19 | GP-041221 | Updated during GERAN #19 (v0.39). | V0.39 |
| 25 June 2004 | G20 | GP-01740 | Updated during GERAN #20 (V0.40) | V0.40 |
| 27 June 2004 | G21 | GP-0XXXX | Updated during GERAN #21 (V0.41) |  |